## Defects
Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
HTML tags not removed completely | Sprint 1 | Developer | Functional | Improved preprocessing rules | 2025-11-27 | Closed | Resolved after regex fix
Spam emails misclassified | Sprint 2 | ML Engineer | Functional | Model retrained with balanced data | 2025-12-12 | Closed | Accuracy improved
Urgent keywords not detected | Sprint 3 | ML Engineer | Functional | Keyword rules updated | 2025-12-26 | Closed | Urgency fixed
Bias towards medium urgency | Sprint 3 | ML Engineer | Performance | Class weight tuning applied | 2025-12-26 | Closed | Balanced output
Dashboard crash on large data | Sprint 4 | Frontend Dev | Performance | Optimization pending | 2026-01-09 | Open | Under analysis

## Sheet2
Logical
User Interface
Maintainability
Standards
Others